## WBS-early draft (hidden)
Work Breakdown Structure
PROJECT TITLE |  | PROJECT TITLE |  |  |  |  | Smart Jacket Development |  |  |  | LEAD INSTITUTION | [6 empty] | University of Rijeka, Faculty of Engineering
PROJECT MANAGER |  | PROJECT MANAGER |  |  |  |  | Miroslav Joler |  |  |  | DATE | [6 empty] | 2019-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | Unit Description | Unit Cost | Quantity | Cost | START MONTH | DURATION (months) // PERIODIC | DUE MONTH // PERIOD | PCT OF TASK COMPLETE | YEAR 1 | [11 empty] | YEAR 2 | [17 empty] | YEAR 3 | [5 empty] | YEAR 4
[17 empty] | project months | [11 empty] | project months | [11 empty] | project months | [11 empty] | project months
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
1 | Personnel Hiring
1.1 | Postdoc hiring | princip. inv. (PI) |  |  |  |  | 1 | 4 | 4 | 0% | bar: 1 to 4
1.2 | PhD student hiring | princip. inv. (PI) |  |  |  |  | 1 | 3 | 3 | 0% | bar: 1 to 3
2 | Equipment Procurement
2.1 | RF Equipment | PI, PA |  |  |  |  | 1 | 6 | 6 | 0% | bar: 1 to 6
2.2 | Textile-related Equipment | PI, PA |  |  |  |  | 1 | 6 | 6 | 0% | bar: 1 to 6
2.3 | IT Equipment | PI, PA | [6 empty] | -1 | 0%
2.4 | Software | PI, PA |  |  |  |  | 3 | 2 | 4 | 0% | bar: 3 to 4
2.5 | Materials and Small Components | PI, PA |  |  |  |  | 4 | 4 | 7 | 0% | bar: 4 to project months 7
2.6 | Office Supplies | PI, PA | [5 empty] | periodic |  | 0% | bar: 5; project months 10; project months 15; project months 20; project months 25; project months 30; project months 35
3 | Advanced Textile Materials Research | [6 empty] | 17
3.1 | Testing conducting and insulating textiles | TTF/Member C |  |  |  |  | 7 | 2 | 8 | 0% | bar: project months 7 to project months 8
3.2 | Investigating optimal threads | TTF/Member C |  |  |  |  | 9 | 2 | 10 | 0% | bar: project months 9 to project months 10
3.3 | Testing washability, water repellency, stretching, wind-proofing | TTF/Member C |  |  |  |  | 11 | 4 | 14 | 0% | bar: project months 11 to project months 14
3.4 | Investigation of textile permittivity and dielectric loss | TTF/Member C |  |  |  |  | 15 | 4 | 18 | 0% | bar: project months 15 to project months 18
3.5 | Innovative jacket design (pockets for HW, wiring) | TTF/Member C |  |  |  |  | 19 | 4 | 22 | 0% | bar: project months 19 to project months 22
3.6 | Submitted publication | TTF/Member C |  |  |  |  | 23 | 1 | 23 | 0% | bar: project months 20; project months 23
4 | Antenna R&D | [6 empty] | 16
4.1 | Antenna design | URI/Member A |  |  |  |  | 7 | 2 | 8 | 0% | bar: project months 7 to project months 8
4.2 | Antenna firmness and elasticity optimization | URI/Member A |  |  |  |  | 9 | 2 | 10 | 0% | bar: project months 9 to project months 10
4.3 | Optimization of connectors: straight, angle, button | URI/Member A |  |  |  |  | 11 | 1 | 11 | 0% | bar: project months 11
4.4 | Washability and water repellency robustness (interactive with WP3) | URI/Member A |  |  |  |  | 13 | 3 | 15 | 0% | bar: project months 13 to project months 15
4.5 | Antenna diversity (two-arm solution) investigation | URI/Member A |  |  |  |  | 12 | 3 | 14 | 0% | bar: project months 12 to project months 14
4.6 | EM shield layers for SAR improvement | URI/Member A |  |  |  |  | 15 | 2 | 16 | 0% | bar: project months 15 to project months 16
4.7 | SAR evaluations on bio-models | URI/Member A |  |  |  |  | 17 | 2 | 18 | 0% | bar: project months 17 to project months 18
4.8 | Antenna design optimization | URI/Member A |  |  |  |  | 19 | 3 | 21 | 0% | bar: project months 19 to project months 21
4.9 | Submitted publication | URI/Member A |  |  |  |  | 22 | 1 | 22 | 0% | bar: project months 18
5 | Body Area Network Development / Sensors Research
5.1 | Micro-processor control development | URI/Member B |  |  |  |  | 7 | 6 | 12 | 0% | bar: project months 7 to project months 12
5.1.1 | Communication with transceivers and antennas | URI/Member B |  |  |  |  | 7 | 1 | 7 | 0% | bar: project months 7
5.1.2 | Duplex voice communication | URI/Member B |  |  |  |  | 8 | 2 | 9 | 0% | bar: project months 8 to project months 9
5.1.3 | Basic communication with sensors | URI/Member B |  |  |  |  | 10 | 2 | 11 | 0% | bar: project months 10 to project months 11
5.2 | Sensors application research | URI/Member B |  |  |  |  | 10 | 3 | 12 | 0% | bar: project months 10 to project months 12
6.2.1 | Heart rate sensor: type and placement | URI/Member B |  |  |  |  | 10 | 1 | 10 | 0% | bar: project months 10
6.2.2 | Blood pressure sensor: size, type, and placement | URI/Member B |  |  |  |  | 11 | 1 | 11 | 0% | bar: project months 11
6.2.3 | Glucose level sensor | URI/Member B |  |  |  |  | 12 | 1 | 12 | 0% | bar: project months 12
5.3 | Peripherals to microprocessor connection optimization | URI/Member B |  |  |  |  | 13 | 3 | 15 | 0% | bar: project months 13 to project months 15
5.4 | Testing of on-body RF links between sensors and processor | URI/Member B |  |  |  |  | 16 | 1 | 16 | 0% | bar: project months 16
5.5 | Submitted publication | URI/Member B | [5 empty] | 0 | -1 | 0% | bar: project months 14; project months 17
6 | Power Supply R&D
6.1 | Power supply by external battery | URI/Member B |  |  |  |  | 12 | 1 | 12 | 0% | bar: project months 12
6.2 | Energy harvesting for battery charging | URI/Member B or F | [5 empty] | 0 | -1 | 0%
6.2.1 | Battery charing by movement | URI/Member B or F |  |  |  |  | 18 | 4 | 21 | 0% | bar: project months 18 to project months 21
6.2.2 | Research on solar cells-covered jacket | URI/Member B or F |  |  |  |  | 21 | 9 | 29 | 0% | bar: project months 21 to project months 29
6.2.3 | Body heat-to-voltage conversion | URI/Member B or F |  |  |  |  | 30 | 10 | 39 | 0% | bar: project months 30 to project months 39
6.3 | Implementation of energy harvesting to battery charging | URI/Member B or F |  |  |  |  | 36 | 8 | 43 | 0% | bar: project months 36 to project months 43
6.4 | Submitted publication | URI/Member B or F | [5 empty] | 0 | -1 | 0% | bar: project months 42
7 | Mobile App Development
7.1 | Mobile app UI development | URI/Member E |  |  |  |  | 17 | 2 | 18 | 0% | bar: project months 17 to project months 18
7.2 | Testing and troubleshooting of mobile app connection to micro-processor and peripherals | URI/Member E |  |  |  |  | 19 | 5 | 23 | 0% | bar: project months 19 to project months 23
7.3 | Speech-to-text conversion and display | URI/Member E |  |  |  |  | 24 | 4 | 27 | 0% | bar: project months 24 to project months 27
7.4 | Text-to-speech conversion and transmission | URI/Member E |  |  |  |  | 28 | 4 | 31 | 0% | bar: project months 29 to project months 31
7.5 | Submitted publication | URI/Member E | [5 empty] | 0 | -1 | 0% | bar: project months 24; project months 28; project months 32
8 | Prototype Manufacturing
7.1 | Making off-clothes antenna prototypes and characteristics measurements | A-E, PI |  |  |  |  | 22 | 1 | 22 | 0% | bar: project months 22
7.2 | Making and testing on-clothes system integration | [5 empty] | 23 | 4 | 26 | 0% | bar: project months 23 to project months 26
7.2.1 | Integrating antenna into jacket | A, B, (C), (F), PI |  |  |  |  | 23 | 2 | 24 | 0% | bar: project months 23 to project months 24
7.2.2 | Integration of power supply, transceiver, processor, sensors etc. | A, B, (C), (F), PI |  |  |  |  | 23 | 2 | 24 | 0% | bar: project months 23 to project months 24
7.3 | Testing, troubleshooting, and optimization with conventional battery | A, B, (C), (F), PI |  |  |  |  | 23 | 4 | 26 | 0% | bar: project months 23 to project months 26
7.4 | Testing, troubleshooting, and optimization with energy harvesting technology, if feasible | A, B, (C), (F), PI |  |  |  |  | 44 | 4 | 47 | 0% | bar: project months 44 to project months 47
7.5 | Submitted publication | [6 empty] | 0 | -1 | 0% | bar: project months 27; project months 47
9 | Dissemination
9.1 | Team meetings | all, PI, PA | [5 empty] | periodic |  | 0% | bar: project months 12; project months 24; project months 36; project months 48
9.2 | Establishing and maintaining a project web page | all, PI, PA |  |  |  |  | 3 | 2 | 4 | 0% | bar: 3 to 4; project months 9; project months 17; project months 25; project months 33; project months 41; project months 48
9.3 | Submitted Conference papers | all, PI, PA | [5 empty] | aperiodic |  | 0% | bar: project months 14; project months 18; project months 20; project months 24; project months 32
9.4 | Submitted Journal papers | all, PI, PA | [5 empty] | 0 |  | 0% | bar: project months 17; project months 23; project months 27 to project months 28; project months 42; project months 47
9.5 | Project Reports | all, PI, PA | [5 empty] | periodic |  | 0% | bar: project months 13; project months 25; project months 37
9.6 | Final report | all, PI, PA |  |  |  |  | 48 | 1 | 48 | 0% | bar: project months 48

## WBS
Struktura projekta po radnim paketima
NASLOV PROJEKTA |  |  |  | Naslov projekta |  | VODEĆA USTANOVA | [6 empty] | Ime ustanove (ako je primjenjivo)
PROJEKTNI AKRONIM |  |  |  | Akronim projekta
VODITELJ PROJEKTA |  |  |  | Ime i prezime voditelja |  | DATUM | [6 empty] | 2022-01-15
BROJ RADNOG PAKETA | NAZIV AKTIVNOSTI | VODITELJ AKTIVNOSTI | POČETNI MJESEC | TRAJANJE (mjeseci) // PERIODIČNO (P) | ZAVRŠNI MJESEC // PERIOD | GODINA 1 | [11 empty] | GODINA 2
[12 empty] | projektni mjeseci | [11 empty] | projektni mjeseci
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Naslov RP1 | Ime voditelja
1.1 |  | Ime izvoditelja |  |  | -1
1.2 |  | Ime izvoditelja |  |  | -1
2 | Naslov RP2 | Ime voditelja
2.1 |  |  |  |  | -1
2.2 |  |  |  |  | -1
-1
3 | Naslov RP3 | xxx
3.1 |  |  |  |  | -1
3.2 |  |  |  |  | -1
4 | Naslov RP4 | xxxx
4.1 |  |  |  |  | -1
-1
5 | Naslov RP5 | xxxx
5.1 |  |  |  |  | -1
5.2 |  |  |  |  | -1